## Sheet1
| Task | To Do | Pending | Stalled | Done | Est. deadline | Comments
1 | Define the deployment Architecture
1.1 | Utilize Docker container technology in the SDTF runtime
1.1.1 | SDTF running in a container |  |  |  | x
1.1.2 | Investigate a single SDTF container for running multiple SDTF suites in parallel | x |  |  |  |  | https://askubuntu.com/questions/505506/how-to-get-bash-or-ssh-into-a-running-container-in-background-mode First answer is relevant
1.1.3 | Investigate how to deploy an SDTF container dynamically |  | 20% |  |  |  | not that clear to me what needs to happen with this, as of now: image with SDTF installed finished;
1.1.4 | Find a way to not get fucked by power outages or machine crashes | x
1.2 | Utilize Selenium grid in the execution of web based test suites
1.2.1 | Set up a selenium grid |  |  |  | x
1.2.2 | Realize all browsers as end nodes to Selenium grid |  | 100% |  | x |  | IE works, but isn't in a container though.
1.2.3 | Investigate the achievability of IE as an end node in a container |  | 100% |  | x |  | Done but not reviewed.
2 | Define a set of IAS WebAdmin test suites to run
2.1 | Define a set of impacted suites |  | 100% |  | x
2.2 | Document the changes necessary |  | 30%
2.3 | Migrate the existing suites to the defined architecture |  | 40% |  |  |  | Currently works for chrome
2.4 | Pull the master into the working branch |  | 99% |  | x |  | Idk, It should be fine? Might not be 100% bug free, so I'm putting it on finished, but not 100%
2.5 | Create a working demo on the test infrastructure | x
2.6 | Create a new Docker image on which the WebAdmin suite works | x |  |  |  |  | I'll probably start on this once the demo works
3 | Documentation and thesis
3.1 | Document the advantages and disadvantages of the proposed changes | x
3.2 | Discuss difficulties encountered with the solution and the used technologies | x
3.3 | Quantify the proposed solution's impact on resources and execution time | x
3.4 | Thesis | [5 empty] | Deadline for final hand-in: 31st of May
3.4.1 | Make a poster (I know right…) | x
3.4.2 | Finish the thesis proposal |  | 100% |  | x |  | Signed and handed in on 07/03/2018
3.4.3 | Prepare for the "tussentijdse evaluatie" | x |  |  |  |  | Presentation on 27/03 at 11:30 in room A118
3.4.4 | Content table | x
3.4.5 | Introduce the company | x
3.4.6 | Introduction (problem statement, goals, etc…) | x
3.4.7 | The rest (to bo defined later on) | x
3.4.8 | Conclusion | x
3.4.9 | Sources | x
3.4.10 | Final presentation | x |  |  |  |  | June, the week of the 25th I think
4 | Stretch goals
4.1 | Deployment
4.1.1 | Browser nodes to be run in non headless mode |  | 70% |  |  |  | Except for IE, I think it’s done? The purpose here is to see what's going on in the browsers, which can be acomplished by running the nodes in debug mode and then going into them using VNC
4.1.2 | Dynamically allocating an SDTF container | x |  |  |  |  | (stuff like kubernetes or docker swarm)
4.2 | Migrate Build Intake suite to the new architecture | x
4.3 | Migrate Radius Authentication suite to the new architecture | x